## Slide 1
Y.J.E. Prencipe
Future Fast Rotorcraft Progress Meeting 02 – 11/10/2023

## Slide 2: Progress Overview Week 5-6 (accounted for 3 weeks studying+exams)
This is week 7 (22/11/23)
Exams went well – passed Electronics, waiting for (positive) result Noise and Emission  kick-off soon?
Gantt chart, to be edited
Writing (a lot) – see Overleaf
  History
  Design Aspects
    ABC, Control sys, AVC
  Modeling
    Rotor inflow
      Lit overview, BET, SMT, LMT (PittPeters, Leishman, ..), Interference Effects, Wake contraction effects, Blade dynamics

## Slide 3: Progress Overview Week 5-6
      Lit overview, BET, SMT, LMT (PittPeters, Leishman, ..), Interference Effects, Wake contraction effects, Blade dynamics
    Propeller modelling
    Fuselage modelling
    Horziontal stabilizer, vertical stabilizer, elevator and rudder modelling
Next:
  more writing: control strategies + control allocation (6-8 days), handling qualities (3-5 days)
  Initial modelling analysis for coax heli as discussed before?
Lit study deadline? – between 1-5 dec without initial modelling, end of year with initial modelling

## Slide 4: Progress Overview Week 5-6
Overall really enjoying the thesis, learning a lot, wishing to learn lots more